## Slide 1: FNSC WORK PLAN JANUARY- DECEmber 2025
Mashonaland Central
NAME OF DISTRICT/ PROVINCE

## Slide 2
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Sensitise District Health Executives on Statutory Instrument 192 of 2024 on breast milk substitutes, Infant and young child feeding regulations | Sensitise 8 DHEs | Number of DHEs implementing the new SI 192 of 2024. | Vehicle, lunch allowances, airtime | 31 March 2025 | Ministry of Health-Nutrition/Environmental health
 | Participation of PFNSC in Provincial development Activities | PFNSC to attend and present on food and nutrition security achievements at 4 PDC meetings (1 per quarter) | Number of PDC meetings attended by PFNSC | Lunches and refreshments | 1 Jan to 31 December 2025 | OPC
 | Indigenous chickens distributed | 40 000 | Number of indegenous chickens distributed | Chicks, stress packs | 1 Jan 25 to 31 Dec 25 | ARDAS
 | Fish Ponds Stocked with Fish | 16 | Number of fish ponds stocked | Fingerlings | 1 Jan 25 to 31 Dec 25 | ARDAS
 | Dams Stocked with fish | 8 | Number of dams stocked | Fingerlings | 1 Jan 25 to 31 Dec 25 | ARDAS
KRA 2
KRA 1

## Slide 3
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Farmers Trained | 440 000 | Number of farmers trained | Training material, fuel, airtime and T&S | 1 Jan 25 to 31 Dec 25 | ARDAS
 | Staff Capacitated | 722 | Number of staff capacitated | Training material, fuel, airtime and T&S | 1 Jan 25 to 31 Dec 25 | ARDAS
 | Maize planted | 235 000 ha | Area planted | Training material, fuel, airtime and T&S | 1 Jan 25 to 31 Dec 25 | ARDAS
 | Winter Wheat planted | 25 000ha | Area planted | Training material, fuel, airtime and T&S | 1 Jan 25 to 31 Dec 25 | ARDAS
 | Small grains planted | 55 000ha | Area planted | Training material, fuel, airtime and T&S | 1 Jan 25 to 31 Dec 25 | ARDAS
 | Crop, Livestock and Fisheries Assessment conducted | 2 | Number of crop and livestock assessments conducted | Training material, fuel, airtime and T&S | 1 Jan 25 to 31 Dec 25 | ARDAS
KRA 2

## Slide 4
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Sweet potato vines distributed | 200 000 | Number of vines distributed | Vines, Vehicle, fuel | 1 Jan 25 to 31 Dec 25 | ARDAS
 | Business units monitored | 26 | Number of business units monitored | Vehicle, fuel, T&S | 1 Jan 25 to 31 Dec 25 | ARDAS
 | Field days Conducted | 220 | Number of field days conducted | Vehicle, fuel | 1 Jan 25 to 31 Dec 25 | ARDAS
 | Famers assisted with PIP inputs | 440 000 | Number of farmers assisted | Input packs | 1 Jan 25 to 31 Dec 25 | ARDAS
 | Tillage. Land preparation, ploughing, Discing, Ripping, Boom spraying. | 125 hectares of land prepared per quarter | Area of land prepared per District | Lubricants,grease,bearings.Fuels 3000 litres | January 1 to march 31 2025 | RIDA
KRA 2

## Slide 5
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 2 | Train community on Climate SMART Agricultural Practices eg Pfumudza | 5000 community members trained on pfumvudza | Number of community members trained on SMART Agriculture Proportion of HH adopting climate | Training materials T&S Vehicle Fuel | APRIL TO NOV 2025 | AGRITEX, EMA, Women Affairs
 | Ward Extension staff capacity building | 176 CDCs | number of Ward extension staff (CDC) trained on FNS issues | Training materials T&S Vehicle Fuel | APRIL TO NOV 2025 | AGRITEX, EMA, Health, Women Affairs
 | Village Business Units Market linkages created | 7 | Markets created | Fuels, T&S, air time | 1 Jan 25 to 31 Dec 25 | AMA
 | IBUs Market linkages created | 7 | Markets created | Fuels, T&S, air time | 1 Jan 25 to 31 Dec 25 | AMA

## Slide 6
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Capacity building on Contract farming and Marketing | 200 farmers trained | Farmers trained on contract farming and marketing | Training material, fuel, airtime and T&S | 1 Jan 25 to 31 Dec 25 | AMA
 | Farmer registration | 5000 | Farmers registered | Fuel |  | AMA
 | Merchants registered | 15 | Merchants registered | Training material, fuel, airtime and T&S | 1 Jan 25 to 31 Dec 25 | AMA
 | Cluster registration | 5 | Number of farmer clusters registered | Training material, fuel, airtime and T&S | 1 Jan 25 to 31 Dec 25 | AMA
KRA 2

## Slide 7
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Weekly commodity bulletins production | 52 | Weekly commodity reports produced |  | 1 Jan 25 to 31 Dec 25 | AMA
 | Reporting on monthly Agro-input monitoring | 12 | Monthly reports produced |  | 1 Jan 25 to 31 Dec 25 | AMA
 | CIDPs/CBPs established | 27 | Number of CBPS/CIDPs established | Training material, fuel, airtime and T&S and clerk salries | 1 Jan 25 to 31 Dec 25 | AMA
KRA 3 | Mobilize communities to Implement livelihood projects that use labour saving technologies | 400 farmer women | Proportion of farmer women accessing labour saving technologies | Training materials Samples of machines Vehicle Fuel | January to December | Mechanization Department, AGRITEX, Irrigation, Women Affairs
KRA 2

## Slide 8
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Rolling out food mitigation program to food insecure population | 762290 people | Proportion of households receiving SP support | Grain, Fuel and T & S | Monthly | Department of Social Development, Agritex, OPC and Local Government.
 | Vulnerable people receiving Cash Transfer | 17800 people | Number of vulnerable people receiving cash transfer | Finance, Netone Lines, Fuel, Vehicles, T & S | Quarterly | Department of Social Development
 | People assisted to access medical services | 100% | Number of people assisted to access medical services | AMTO Books, Finance for hospital bills, Fuel and T & S | Quarterly | Department of Social Development and Ministry of Health and Child Care
KRA 3

## Slide 9
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Piggery project for Mazowe River Bridge Old Peoples Home | 20 people | Proportion of people benefiting from income generation and consumption | Pigpen, Piglets, piglets feed and servicing sows. | Quarterly | Department of Social Development. Mazowe Old Peoples Home
 | Chicken project for Mazowe River Bridge Old Peoples Home | 20 people | Number of people benefiting from income generation and consumption | Chicks, poultry feed and vaccine | Quarterly | Department of Social Development. Mazowe Old Peoples Home. VET
 | Egg Production project for Kutenda Children’s Home | 30 people | Number of people benefiting from income generation and consumption | Layers, Layers feed and vaccines. | Quarterly | Department of Social Development, VET and Kutenda Children’s Home.
KRA 3

## Slide 10
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Goat Breeding project for Kutenda Children’s Home | 30 people | Number of people benefiting from income generation and consumption | Goat feed, vaccines. | Quarterly | Department of Social Development, VET and Kutenda Children’s Home.
 | Horticulture project for Kutenda Children’s Home | 30 people | Number of people benefiting from income generation and consumption | Seeds, herbicides and fertilizers. | Quarterly | Department of Social Development, VET and Kutenda Children’s Home.
 | Piggery project for Mazowe River Bridge Old Peoples Home | 20 people | Proportion of people benefiting from income generation and consumption | Pigpen, Piglets, piglets feed and servicing sows. | Quarterly | Department of Social Development. Mazowe Old Peoples Home
KRA 3

## Slide 11
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 3 | Poultry project for Ponesai Vanhu Childrens Home | 70 people | Number of people benefiting from income generation and consumption | Chicks, poultry feed and vaccine | Quarterly | Department of Social Development. Mazowe Ponesai Vanhu Children’s Home and VET.
 | Rabbit project for Ponesai Vanhu Childrens Home | 70 people | Number of people benefiting from income generation and consumption | Rabbits, Rabbits pellet and vaccines | Quarterly | Department of Social Development. Mazowe Ponesai Vanhu Children’s Home and VET.
 | Poultry project for Ponesai Vanhu Childrens Home | 70 people | Number of people benefiting from income generation and consumption | Chicks, poultry feed and vaccine | Quarterly | Department of Social Development. Mazowe Ponesai Vanhu Children’s Home and VET.

## Slide 12
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Horticulture project for Ponesai Vanhu Children’s Home | 70 people | Number of people benefiting from income generation and consumption | Seeds, herbicides and fertilizers. | Quarterly | Department of Social Development, VET and Ponesai Children’s Home.
 | Piggery project for Ponesai Children’s Home | 70 people | Number of people benefiting from income generation and consumption | Pigpen, Piglets, piglets feed and servicing sows. | Quarterly | Department of Social Development, VET and Ponesai Children’s Home
 | Identify and establish production units in VTCs | 4 production units | Number of production units and direct beneficiaries | Transport, fencing, Livestock, seeds for agriculture | On going | MYEDVT -ZYC DSD ARDAS
KRA 3

## Slide 13
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Capacitation of health staff on food inspection. | All public health officers in the province | % coverage of health staff capacitated by district. | Food and allowances for the cluster meetings | 31 December 2025 | Ministry of Health-environmental health
 | Engagement of sector ministries on food safety for a health nation. | Law enforcement agents, policy markers, AREX, Vert. officers, and Public health officers (Collaboration or integration) | Number of ministries reached. | Refreshments | 31 March 2025. | Ministry of Health(Environmental health), ZRP
 | Coordinate the training of food handlers in all the 8 districts. | 8 districts | Number of districts with food handlers trained with approved certificates | Stationery, allowances and teaching aids | 31 December 2025 | Ministry of health-environmental health
 | Facilitate food inspection on trading and non trading premises to control food contamination and poisoning. | All food processing and and food outlets for public consumption | Number of food outlets inspected | Stationery | Quarterly food mop up. | Ministry of Health- Environmental health
KRA 4

## Slide 14
Key Result Area` | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Investigation of rumours and any food poisoning report. | 100% reports of food poisoning to be investigated | % of reported cases of poisoning adequately investigated with written reports | Fuel and allowance for staff | 31 December 2025 | Ministry of health-environmental health
 | Prosecution of offenders and destroying unwholesome food stuffs. | 100% of all prosecutions with written reports | Proportion of reports with prosecution reports made. | Prosecution forms. | 31 March 2025 | Ministry of health-environmental health, ZRP
 | Introduce food security screening at borders to prevent food related risks, ensure compliance with regulations. | 2 border posts (Kanyemba and Mukumbura) | Number of border posts with food security screening | Prosecution and detention forms | 30 June 2025 | Ministry of health-environmental health and ZIMRA
 | Train households to build tippy taps (hand washing facilities) | 5000 households | Proportion of households with hygiene enabling facilities | Chigubhu gear Cement, builders | January to December | Health and Child Care, RIDA, Women Affairs
KRA 4

## Slide 15
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 5 | Capacitate health workers on Integrated Management of Acute Malnutrition(IMAM) | Train 15 nurses in Centenary on IMAM Outpatient Therapeutic program. Train 20 nurses on IMAM OTP program in Mbire. | Number of health workers trained on IMAM OTP program Cure rate for acute malnutrition | IMAM guidelines, training material, DSA for trainers, vehicle and fuel | 31 March 2025 for Centenary district and 31 October for Mbire district | Ministry of Health, World Vision Muzarabani AP, ACF/NAZ/IMC consortium
 | Improve quality of care in stabilization centres (SC) for IMAM | Refurbish Chitsungo mission hospital stabilization Centre Train 5 stabilization centre staff (doctors and nurses on IMAM SC) | Number of IMAM stabilization centres refurbished Number of SC staff trained on IMAM OTP Number of children successfully stabilized/cured in SC | SC centre requirements( equipment, medicines and supplies, utensils etc) | 31 October 2025 | Ministry of Health ACF/NAZ/IMC consortium
 | Strengthen capacity of community health workers to identify and refer malnutrition cases in the community | Support 296 Village health workers in Shamva and 266 Village Health workers in Rushinga on Mid-Upper Arm Circumference screening program. | Number of Village Health Workers received supported on MUAC screening program. Number of children reached with active screening | 2 vehicles( 1 provincial and 1 district vehicle), DSA for 3 provincial cadres for 5 days per month, DSA for 4 district cadres for 10 days per month, 2100 Litres of Diesel ,MUAC tapes, $10 airtime for 7 people per month | 31 March 2025 | Ministry of Health

## Slide 16
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Support and supervise districts on implementation of care groups and Infant and Young Child Feeding support groups | 2 districts visited and supported on care groups and IYCF support groups per quarter | Number of districts implementing care groups and IYCF support groups | Vehicle and fuel (800litres of diesel), DSA for supervisors | Quarterly | Ministry of Health-Nutrition
 | Support districts on nutrition supply chain management | 3 districts visited quarterly to check on availability, quantity and expiry dates of nutrition commodities at district level. | Number of districts supported on nutrition supply chain management. Number of districts reporting no stock outs or expiries of nutrition commodities. | Vehicle, lunch allowance and fuel | Quarterly | Ministry of Health-Nutrition
 | Support implementation of school nutrition program | 1 district (Rushinga, Bindura or Mt Darwin ) visited and supported on school nutrition program per quarter. | Number of districts visited and supported on school nutrition program. Number of schools providing 4 star diet meals. Number of schools with tuckshops selling healthy foods and snacks. | Vehicle, lunch allowance, fuel | Quarterly | Ministry of Health-Nutrition/environmental health/nursing MoPSE
KRA 5

## Slide 17
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Strengthen integrated outreach activities including nutrition activities (Screening for malnutrition, Vitamin A supplementation etc) for hard to reach areas | At least 1 district conducting integrated outreach services to hard to reach communities per quarter | Number of children receiving nutrition services during integrated outreach activities. Number of integrated outreaches conducted. | Vehicles, DSAs for outreach teams, fuel | Quarterly | Ministry of Health
KRA 6 | Participate in food and nutrition security data collection, timely information dissemination, utilization and feedback | Extension workers from 8 districts collecting, analyzing , reporting and utilizing information on food and nutrition security | Number of sectors participating in data collection, analysis, reporting and timely information dissemination, utilization and feedback | Vehicles, DSAs, Fuel, stationery,allowances | Quarterly | , Women affairs, ministry of youth Local government, Ministry of health, DSD,AGRITEX
KRA 7 | Joint water quality monitoring visits | One water point per District/quater | Number of Districts visited to assess water quality | Vehicles and fuels,200 litres | Quarterly January 1 to March 31 2025. | RIDA, HEALTH
KRA 5

## Slide 18
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 7 | Strengthen Provincial Food and Nutrition Security committee coordination | Provincial food and nutrition security committee quarterly meetings | Number of PFNSC meetings conducted. | Lunches and refreshments, projector, Stationery, printer and laptop | Quarterly | All PFNSC members, ACF consortium, CTDO and other partners in the province
 | Conduct Monitoring Visits to Community and nutritional gardens/ projects | 8 community gardens per quarter | Proportion of Joint monitoring of FNS projects at provincial level | T&S Vehicle Fuel | 1 December to 31 December 2025. | Agritex , women affairs, ministry of health
 | 1.Ward Extension staff capacity building 2.Capacity building on Citizen Journalism | -119 Ward Youth Coordinators - 34 Jnr MPs - 232 Jnr Councilors | -Number of Ward Youth Coordinators -Number of Jnr MPs -Number of Jnr Councilors | Food and refreshments -Stationary -Allowance -Transport -Bus fares -Accommodation | March to August | Ministry of youth -Zimbabwe Youth Council -Vocational Training centres -ARDAS -MOPSE

## Slide 19
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 7 | Promote production, preservation and utilization of locally available nutritious foods | Conduct 1 cooking contest or food fair per quarter | Number of cooking competitions and food fairs conducted | Food items, utensils, prices, fuel for cooking, venues | On going | -MYEDVT -ZYC -ARDAS -MOHCC -MOWACD -MOPSE -VTCs