Harare Provincial Food and Nutrition Security Committee

Work plan 2020

| FNSP Commitment & Strategic objective: 5. Nutrition Security (MOHCC) | Key district activities | Inputs | Key partner agencies | Timeline | Budget |
| --- | --- | --- | --- | --- | --- |
| - Infant and Young Child Nutrition | - Train health workers and Nutrition volunteers on IYCF counselling - Train Community Health Workers on CIYCF counselling - Quarterly visits by province. - Community cooking demonstrations | Fuel (300L per district) Funds(DSA) Stationery(3 boxes pens, 10 reams, 2 toners,) | - UNICEF - MoHCC - Chiedza - Social services - Nutrition - Environment | All year round |  |
| - Maternal Nutrition | - Screening of pregnant women for malnutrition - Counselling pregnant women on maternal nutrition - Referring malnourished pregnant and lactating women to Social Services for food assistance - Community cooking demonstrations | Height boards Scales Muac tapes Stationery | - Department of Social Services - Grain marketing Board - UNICEF | All months |  |
| - Micronutrients | - Conduct ECD and Crèche Vitamin A supplementation and Community outreaches - Conduct routine iodine monitoring - Nutrition education at health facilities, community and schools to promote the consumption of dietary sources of Vitamin A, Iron and Folate and fortified foods. - Nutrition education at health facilities to promote compliance of Iron/Folate supplementation | Fuel Funds IEC material | Nutrition Nursing Health Promotion UNICEF | Jan-June |  |
| - Growth monitoring and promotion | - Routine growth monitoring of children under- fives at health facilities - Community outreach for EPI services for hard to reach areas - Community active screening for malnutrition through the Family led MUAC initiative and refer to health facility |  |  |  |  |
| - Management of Acute Malnutrition | - Screen and manage severe and moderately malnourished children at the health facility - Follow up defaulters at community level - refresher training for CHWs and Health workers on IMAM - Mentorship visits | 300L Fuel per district | UNICEF | All months | $2000-00 |
| - Management of Non Communicable diseases | - Community wellness programs - Nutrition Counselling at health facility to NCD patients - Sensitisation on prevention and management of NCDs to the community. |  |  |  |  |
| - School Health program | Nutrition assessment of school going children Training of school health masters on child and adolescent nutrition School feeding program |  |  |  |  |

| FNSP Commitment & Strategic objective | Key District Activities | Inputs | Key Partner Agencies | Timeline | Budget($) |
| --- | --- | --- | --- | --- | --- |
| 2.3 Implement sustainable food production strategies that promote enhanced production in the context of managing risk as a result of climatic change | 1. Promote adoption of technologies such as C.A, land reclamation and water harvesting. Adoption of Pfumvudza concept | Fuel per district Stationary | City councils Local Boards ZFU Forestry commission EMA BRDC Communities NGOs Schools Health Centres Women affairs | October 2020 to September 2021 |  |
|  | 2. Promote establishment of orchards in schools, hospitals and community centres as well as at household levels. | fruit trees (potted) |  |  |  |
|  | 3. Promote an increase in production of small livestock (rabbitry and poultry). |  |  |  |  |
|  | 4. Promote an increase in the establishment of backyard gardens at household level. Community gardens at community centres. |  |  |  |  |
| 2.4 Equip farmers with technology and approaches that help mitigate the adverse effect of unreliable rainfall pattern in Zimbabwe and the broader effects of climatic change. | 1.To rehabilitate Sinansengwe (Binga) Mazamnyama canal and three schemes (Tsholotsho), Lukosi(Hwange) irrigation scheme. |  | FAO MoESAC MoHCC MoHA GMB FEWSNET ZFU Lead Trust Save the children KMTC ZimSTAT MoLSS MoLGURD BRDC Veterinary services Local authority | Oct 2020 to March 2021 | 74250 |
|  | 2. To lobby for Input support in all irrigation schemes. |  |  |  |  |
|  | 3. To lobby for fast completion of 5000ha in Bulawayo kraal irrigation scheme. |  |  |  |  |
|  | 4. To conduct trainings so as to cascade the early warning information to farmers. |  |  |  |  |
| FNSP Commitment & Strategic objective | Key District Activities | Inputs | Key Partner Agencies | Timeline | Budget($) |
| 2.3 Implement sustainable food production strategies that promote enhanced production in the context of managing risk as a result of climatic change | 1. Promote adoption of technologies such as C.A, land reclamation and water harvesting. | 300L fuel per district Stationary | ZFU Forestry commission EMA BRDC Communities NGOs Schools Women affairs |  |  |
|  | 2. Promote integrated forest farming, fruit farming, agricultural and fish farming systems at household and community levels. |  |  |  |  |
|  | 3. Promote an increase in production of small livestock (shoats, pigs and poultry). |  |  |  |  |
|  | 4. Promote an increase in the production of small grains. |  |  |  |  |
| 2.4 Equip farmers with technology and approaches that help mitigate the adverse effect of unreliable rainfall pattern in Zimbabwe and the broader effects of climatic change. | 1.To rehabilitate Sinansengwe(Binga)Mazamnyama canal and three schemes(Tsholotsho), Lukosi(Hwange) irrigation scheme. |  | FAO MoESAC MoHCC MoHA GMB FEWSNET ZFU Lead Trust Save the children KMTC ZimSTAT MoLSS MoLGURD BRDC Veterinary services Local authority |  |  |
|  | 2. To lobby for Input support in all irrigation schemes. |  |  |  |  |
|  | 3. To lobby for fast completion of 5000ha in Bulawayo kraal irrigation scheme. |  |  |  |  |
|  | 4. To conduct trainings so as to cascade the early warning information to farmers. |  |  |  |  |
| 2.5 Strengthen post-harvest management and household storage techniques through investment and training that will result in the reduction in post harvest losses and so increase the efficiency on the food chain | 1. Promote use of improved grain storage structures and preservation measures at household level. 2. To lobby for granary construction for 39 chiefs under Isiphala seNkosi (28 in ECHO districts) |  | MoHCC |  | 10000 |
|  | 3. Adequate recruitment and strengthening capacity of agricultural and health extension officers in pre and post harvest management through pre and in-service training and involvement of private sector for training services. |  |  |  |  |
| 2.7 Ensure that agriculture and other income generating interventions are components for assisting chronically vulnerable, including those affected by HIV/AIDS and TB. | 1. Promote adoption of technologies such as C.A and water saving gardens. |  | MoHCC FNSC NGOs BRDC GMB ZFU Local authority Women affairs |  | 15000 |
|  | 2. Ensure that extension services and alternatives are put in place for PLWHIV/AIDS and TB. |  |  |  |  |
| FNSP Commitment & Strategic objective | Key District Activities | Inputs | Key Partner Agencies | Budget($) |  |
| Ensure all social assistance is timely and meets universally accepted minimum standards | Food Assistance for vulnerable groups |  | WFP Social services |  |  |
|  | Cash Transfers for vulnerable groups |  |  |  |  |
|  | Supplementary feeding programmes for vulnerable groups |  |  |  |  |

| FNSP Commitment & Strategic objective | Key Activities | Inputs | Key Partner Agencies | Timeline | Budget($) |
| --- | --- | --- | --- | --- | --- |
| FNSC functions | - Mobilisation of stakeholders, local leadership, church elders and residents and selection of ward committee | Fuel per month per district DSA for 3 |  |  |  |
|  | - Training workshops of Ward FNSC | 300l IEC material Refreshments Mobile Internet |  |  |  |
|  | - Monitoring and evaluation of programmes | 400L per district DSA |  |  |  |
|  | - Monthly meetings | Fuel Lunches Mobile Internet |  |  |  |
|  | - Quarterly review workshops PFNS and DNSC | 300l IEC material Refreshments Mobile Internet |  |  |  |