MANICALAND

PROVINCIAL FOOD AND NUTRITION SECURITY COMMITTEE (PFNSC)

2025 ANNUAL WORKPLAN

- Policy Analysis and Advice

| KRA | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Monthly review and coordination meetings | 12 | Number of meetings conducted | Allowances, stationery ,fuel | Monthly | Min of Agriculture ,DSD,MOHCC |
| 1 | Quarterly PFNSC monitoring visits to Districts | 1 monitoring visit per quarter | Number of provincial monitoring visits | Fuel, Lunches | Quarterly | Min of Agriculture ,DSD,MOHCC |
| 1 | Support DFNSC meetings in 7 districts | 7 support visits | Number of monitoring visits | Lunch allowance | June/July | CTDO, CARE, World Vision |

2.0 Nutrition Sensitive Agriculture

| KRA | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency/Supporting Agencies |
| --- | --- | --- | --- | --- | --- | --- |
| 2 | Scaling up training of farmers and mainstreaming nutrition into Agricultural activities | 500 extension officers | Number of extension officers trained | Food Fuel Bus fares Allowances stationery | 1st and 2nd Quarter | Agritex, |
| 2 | Training farmers on Climate Smart Agricultural Practises e.g. Pfumvudza | 150000 | Number of farmers trained | Fuel, Flip boards and charts, mighty markers | 2nd to 3rd Quarter | Agritex |
| 2 | To participate in field days and shows | 20 field days 9 shows | Number of field days held Number of shows held |  | 1st to 3rd Quarter | Agritex ,GVT Departments and NGOS |
| 2 | Conduct training to Promote and increase in production of small livestock (sheep, goats, pigs and poultry) | 150000 | Number of farmers trained | Food Fuel Bus fares Allowances Stationery | 1st and 4th Quarter | Agritex |
| 2 | Winter wheat planting | 1000ha | Number of hectares planted | Registers, Transport,airtme | 2nd Quarter | Agritex |
| 2 | Complete the development of a provincial agricultural calendar | 1 | Provincial agricultural calendar developed | Food Fuel stationery | Q1 | Agritex |
| 2 | Training of young farmers on dairy production | 500 | Number of young farmers trained |  | Q1 | Youth,ILO, Agritex, |
| 2 | Training lead farmers on healthy harvest and agro ecological gardening | 100 | Number of lead farmers trained | Training material, Lunch | Q2 and Q3 | CTDO |
| 2 | Support farmers at demo sites to reinforce skills and trouble shoot | 55 | Number of demo sites supported | Seeds | On-going | AGRITEX |
| 2 | Strengthening the Zunde Ramambo concept in Makoni and revive in Nyanga district | 2 | Functional Zunde Ramambo community initiatives | Food Fuel Stationery | Q2 and Q3 | AGRITEX |

3.0 Nutrition Sensitive Social Protection

| KRA | ACTIVITY | TARGET | PROCESS INDICATOR | RESOURCES | TIMELINE | LEAD AGENCY |
| --- | --- | --- | --- | --- | --- | --- |
| 3 | Monitor distribution of social assistance to the communities by partners | All 7 districts | Number of monitoring visits done | Fuel Allowances Stationary | Q1-Q4 | DSD |
| 3 | Train Schools on the School Nutrition Programme | 730 Primary schools 289 Secondary schools | Number of Schools implementing School Nutrition Programme | Fuel Bond paper Promotional IEC materials Allowances | Q2-Q4 | MOPSE |
| 3 | Facilitate the formation of School Health clubs | 500 health clubs | Number of school health clubs | Fuel Participatory Health and Hygiene Education (PHHE) tools Bond paper Promotional IEC materials Allowances | Q2-Q4 | MOPSE, MOHCC, |
| 3 | Establish projects for persons with disabilities | 3 projects per district | Number of projects established | CDCs | Q1-Q4 | DSD, ARDAS, Women Affairs, Youths, |

4.0 Nutrition Sensitive Food Safety and Standards

| Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- |
|  | Capacity strengthening of Health Clubs on PHHE | 1500 | Number of people trained in PHHE Number of households with functional hygiene enabling facilities | Fuel, Bond paper, Allowances Training material | Q1-Q4 | MOHCC, Care International |
| 4 | Enforce compliance and certification of all locally produced and imported foods | 95% | Proportion of compliance reported | Fuel, Bond paper, Promotional I.E.C material, allowances | Q1-Q4 | MOHCC |
| 4 | Construction of self-supply latrine building to improve sanitation coverage | 400builders 1500 latrines | Number of latrine builders trained Number of latrines constructed | Training materials, trained latrine builders | Q1-Q4 | MOHCC, CTDO , Local Authorities |
| 4 | Conduct ambient water sampling | 500 samples | Number of samples tested | Sampling bottles ,T&S ,Fuel, PPE, Freighting | Monthly | MOHCC |
| 4 | Facilitate drilling and installation of new boreholes | 547 boreholes | Number of boreholes | Drilling consumables, PPE, Allowances | Q2-Q4 | RIDA, ZINWA, Local Authority, MOHCC |
| 4 | Facilitate borehole rehabilitation (hand pumps) | 533 | Number of boreholes | Drilling consumables, PPE, Allowances | Q2-Q4 | RIDA, ZINWA, Local Authority, MOHCC |
| 4 | Distribution of NFI kits | 10785 | Number of NFI kits distributed | Fuel Stationery Allowances | Q2-Q4 | MOHCC, Local Authority, |
| 4 | Facilitate rehabilitation of piped water schemes | 87 | Number of piped water schemes rehabilitated | Fuel, rehabilitation consumables, Allowances | Q2-Q4 | MOHCC, Local Authority, |
| 4 | Facilitate rehabilitation of waste water treatment plants | 10 | Number of waste water treatment plants rehabilitated | Fuel, rehabilitation consumables, Allowances | Q2-Q4 | MOHCC, Local Authority, |

5.0 Nutrition Security

| Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- |
| 5 | Training of health workers on IMAM in Mutare and Nyanga | 2 | Number of health workers trained | Fuel Bond paper Allowances Conference Facility | Q2 ,Q3 | MOHCC |
| 5 | Supplement at least 85% of children with Vitamin A | 85% | Proportion of Children receiving Vitamin A | Vitamin A Capsules M&E tools | Monthly | MOHCC, UNICEF |
| 5 | Facilitate establishment of Care Groups in 6 Emergency districts (Chipinge, Buhera, Mutare, Nyanga , Chimanimani and Makoni) | 12300 | Number of Care Groups established | Fuel Vehicle Scales Stationery Allowances | Q2 ,Q3 | MOHCC, Care International, CTDO |
| 5 | Conduct Integrated outreach services in all the 7 districts | 7 districts | Number of outreaches done | Essential Medicines, Supplies, Visibility materials, Doctor, Allowances, Fuel, Ambulances | Q1-Q3 | MOHCC, UNICEF |
| 5 | World Breastfeeding week commemorations | 7 | Number of districts conducting WBW commemorations | IEC Materials Fuel Vehicles Allowances | August | MOHCC, UNICEF |
| 5 | Iron folic acid(IFA) supplementation to in school adolescents in (Nyanga and Makoni) | 104663 | Number of adolescents receiving IFA | IFA tablets Hb machines Logistical Support ICT(smart phones) for reporting purposes | 1st and 2nd term | MOHCC/MOPSE |
| 5 | Supporting mothers/caregivers in care group activities with a focus on the health and nutrition priority behaviours | 20,000 | Number of mothers/caregivers participating in care group activities | Care group sessions | December | MOHCC, Care International |
| 5 | Cooking demos conducted with mothers/caregivers to promote nutritious locally available food. | 11000 | Number of cooking demos conducted | Recipe guides | December | MOHCC, Care International, Women Affairs |
| 5 | Coaching and mentoring of Male champions on nutrition activities and supporting male peers. | 500 male champions 5,000 male peers | Number of Male Champions coached and mentored Number of male peers supported | Coaches and Mentors | December | Women Affairs, Care International ,MOHCC, |
| 5 | Establishment of Micro-gardens | 5,000 | Number of Micro-gardens established by mothers/caregivers | Healthy harvest trainings | December | Agritex, MOHCC, EMA, Local Authorities |

6.0 Food and Nutrition Information Assessment, Analysis and Early Warning

| KRA | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- |
| 6 | Crop and livestock data collection | 3 (1st ,2nd and 3rd round) | Number of assessments done | Fuel, Allowances Airtime, Smart Phones, | 1st and 2nd Quarter | ZIMSTAT, Agritex |
| 6 | Participation in the national food and nutrition security data collection(ZMLAC) | 2 (Urban and Rural) | Number of assessments done | Fuel, Allowances Airtime, Smart Phones, | 1st and 2nd Quarter | OPC,DSD, LA,MOHCC, Agritex,MLG, Partners |
| 6 | ZMLAC information dissemination | 2 (Urban and Rural Assessment) | Number of dissemination meetings conducted | Fuel,Allowances | 2nd and 3rd Quarter | OPC,DSD, LA,MOHCC, Agritex,MLG, Partners, Information |

7.0 Enhancing and Strengthening Capacities for Food and Nutrition Security

| Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- |
| 7 | Training of PFNSC members | 35 | Number of member trained | Conference, Allowances | Q2 | FNC, OPC,Agritex, DSD,MOHCC,LA |
|  | Training of PFNSC on ECD | 35 | Number of member trained | Conference, Allowances | Q2 | FNC, OPC,Agritex, DSD,MOHCC,LA |
| 7 | Refresher training of 5 DFNSCs ( Chimanimani, Makoni, Nyanga, Mutasa and Mutare) | 5 | Number of districts trained | Conference, Allowances, Fuel | Q3 | FNSC, OPC,Agritex, DSD,MOHCC,MLG |
| 7 | Support refresher training of WFNSCs in 5 Districts ( Chimanimani, Makoni, Nyanga, Mutasa and Mutare) | 7 Committees | Number of WFNSCs trained | Stationery, refreshments Lunch allowances | Q1 | FNC, OPC,Agritex, DSD,MOHCC,MLG,CTDO |
| 7 | Training of women on ISALS | 50 ISAL groups | Proportion of HH participating in ISALs Number of groups trained. | Refreshments, stationery, lunch allowances | Q1-Q4 | Women Affairs. |
| 7 | Participate in national cookout competition | 1 per each district 1 Provincial event | Number of cookout competitions held | Competitors | Q 1-Q2 | Women Affairs |