## Slide 1: FNSC WORK PLAN JANUARY- DECEmber 2025
MASH EAST
NAME OF DISTRICT/ PROVINCE

## Slide 2
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 1 | Rhizobium inoculant production | 60000 | Number of rhizobium inoculants availed | Inoculant production raw materials and equipment | February to December 2025 | SPRL
KRA 2 | Maintenance of microbial Strains (Rhizobium, Phosphate Solubilizing Bacteria and Mycorrhiza. | 400 | Number of rhizobia strains sub cultured | Production raw materials and equipment | January to December 2025 | SPRL
KRA 2 | Agriculture Machinery Availability | 95% | Percentage of functional tractors over the total population of tractors | Spare parts and components | Jan-Dec | DAEMFID Private sector
 | Farmers / operators trained on Farm Machinery, Post Harvest Technologies, and Soil Conservation | 4938 | Number of Farmers/ operators trained | Training materials and manuals Partnerships and Collaborations | Jan-Dec | DAEMFID
 | Mechanized Tillage Services | 310 000 | Number of hectares tilled | Fuels and Lubricants | Jan-Dec | DAEMFID Other government departments
KRA 3 | Soil testing And analysis | 100 | Number of soil samples analysed | Soil testing equipment and reagants | January to December 2025 | SPRL
KRA 4 | Evaluation of new or alternative microbial inoculants | 4 | Number of research trials established | As per experiment protocol | January to December 2025 | SPRL
 | Training of clients/Stakeholders on soil fertility management | 400 | Number of students and stakeholders trained | Training personnel and training aids | January to December 2025 | SPRL

## Slide 3
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 1 | Facilitate development of Ward response strategies to food and nutrition security priorities Business units Promotion of small grains Nutritional gardens. | 100 Business units. Pearl millet 10 000 ha Finger millet 5 400 ha In all 9 Districts | Number of Wards with response strategies to food and nutrition security issues All 9 Districts | Gvt and partners inputs support Training materials | Jan-Dec | Agritex
 | Conduct Monitoring Visits to Food and Nutrition projects | 9 Districts | Proportion of Joint monitoring of FNS projects at ward level | Fuels and vehicles. | Jan-Dec | Agritex All Gvt departments NGO,S
KRA 2 | Train Farmers on Sugarbean Maize Sorghum Wheat Soyabeans Sunflower irish potato sweet potato. | 9 Districts 650 000 farmers Sugar Beans 10 960 ha. Maize 240 000 ha. Sorghum 27 500 ha. wheat 21 000 ha. Sunflower 20 000 ha. Soyabeans 11 000 ha. Irish potato 1 200 ha. Sweet potato 4 160 ha. | Number of farmers trained 650 000 | Fuels and vehicles. Training aids and human resource. Gadgets | Jan-Dec | Agritex and relevant stakeholders ie Input suppliers, seed houses and agro-chemical companies.

## Slide 4
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 2 | Ward Extension staff capacity building | 673 extension officers 64 extension supervisors | 737 extension staff trained | Fuels and vehicles. Training aids and human resource. Gadgets Research articles Online courses Recent Agric practices | Jan- Dec | Agritex and relevant stakeholders
 | Diversified Crop & livestock Inputs distribution All 9 Districts receive Presidential inputs for crops and livestock. | 9 Districts 650 000 farmers | Quantity of inputs distributed by type Compound D 5938 mt Top dressing 4643 mt Maize seed 2311 mt Sorghum seed 165 mt Sugar beans seed 143 mt Sunflower seed 90 mt Soya bean seed 77 mt Ground nuts seed 48 mt Number of households receiving Compound D 177 808 hh Top dressing 140 024 hh Maize seed 361 434 hh Sorghum seed 78 059 hh Sugar beans seed 67 940 hh Sunflower seed 36 813 hh Soya bean seed 15 360 hh Ground nuts seed 17 054 hh input packs/livestock Number of Ha planted | Gvt inputs support Inventory management tools Input track system. Transport facilities Partnership with suppliers | April -Jan | Agritex and local leaders

## Slide 5
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 2 | Pest & Disease control (Scouting, surveillance, vaccinations, dipping) |  | Number of animals vaccinated Quantity of dip chemicals supplied |  |  | 
 | Promote Climate SMART Agricultural Practices Pfumvudza/CA Drip irrigation/ water harvesting technics Diversified farming Agro-ecological matching | Train 650 000 farmers across the Province. | Number of CSA techs adopted Four Proportion of HH adopting climate smart tech 600 000 fhh | Gvt support Field trials | Jan-Dec | Agritex and other Gvt departments
 | Promote Climate SMART Agricultural Practices eg Pfumudza | 100 schools | Number of Schools adopting climate smart Agriculture-Pfumvudza | Inputs | Annually | MoPSE in partnership with Agritex
 | Strengthen health and nutrition programmes in schools | 400 schools | Number of schools with feeding places | Cement, bricks, locally available materials | Quarterly | MoPSE

## Slide 6
Key Result Area | Activity | Sub activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 3 | Promote Schools to implementing Home Grown School Feeding Programme | Facilitate Schools implement Home Grown School Feeding | 400 Schools | Number of schools with Home Grown School Feeding Programme | Inputs Hectrage for farming | quarterly | MoPSE
 |  | Conduct Monitoring Visits to Schools to monitor school feeding | 60 Schools | Schools monitored | Motor Vehicle T & S | Termly | MoPSE
 | Rolling out food mitigation program to food insecure population |  | 960256 | Proportion of households receiving SP support | Grain Transport funds T and s | 3 months | DSD
 | Implement livelihood projects that use labour saving technologies |  | 2 | Proportion of farmer women accessing labour saving technologies | Funds Project equipment | 12 months | DSD
KRA 4 | Enforce compliance and certification of all locally produced and imported foods | Conduct food samples analysis with field kits (food fortification, iodine tests etc.) | 1875 | Number of food samples analyzed | Test kits Fuel | Quarterly | MOHCC,
 |  | Collection of food samples & sending to Govt Analyst | 1500 | Number of samples collected and sent to govt analyst | Food samples Fuel | Quarterly | MOHCC
 |  | Conduct food premises inspections. | 1000 | Number of prosecutions done | Fuel | Annually | MOHCC Local authority ZRP
 | Increase awareness on household hygiene, sanitation, and waste management among communities through use of participatory approaches | Train households to build tippy taps (hand washing facilities) | 15% (from 5% ZIMLAC report) | Proportion of households with hygiene enabling facilities | DSAs Fuel Refreshments | 2nd quarter | MOHCC P/DWSC
 |  | Conduct WASH behavior change awareness campaigns | 4 | Number of people reached with WASH behavior change awareness campaigns | Fuel Refreshments | Monthly | MOHCC

## Slide 7
Key Result Area | Activity | Sub Activities | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 5 | Capacity strengthening of stakeholders in IYCF (health workers, caregivers, community leaders, etc) | Capacity building of health workers on Combined IYCF and Growth Standard Training for Health Workers | 6 districts (Chikomba, Goromonzi, Marondera, Hwedza, Mudzi, & UMP | Number of wards/PHC facilities providing IYCF services | DSAs Fuel Refreshments | 3rd quarter | MOHCC
 |  | Scale up Care Group training in all wards in Mudzi and Mutoko districts and expand to other districts | All wards in Mudzi and Mutoko & 5 wards per district (Seke, Marondera and Goromonzi) | Number of wards implementing (care groups, support groups, PHCs, etc) | DSAs Fuel Refreshments | 2nd quarter | MOHCC
 |  | Conduct monthly cooking demonstrations with communities | All wards in Mudzi and Mutoko districts | Number of cooking demonstrations | Food stuffs, Fuel | Monthly | MOHCC
 | Strengthen health and nutrition programmes in institutions of care (schools, correctional services, waiting mothers shelters, old peoples’ homes, etc.) | Capacity building of Health Care Workers and School Health Masters on the School Nutrition program | 400 schools | Number of schools capacitated on the School Nutrition Program | DSAs Fuel Refreshments | 2nd quarter | MOPSE & MOHCC
 |  | Train teachers on school nutrition | 180 teachers | Number of teachers trained | Refreshments T & S vehicle | Termly | MoPSE & MoHCC
 |  | Monitoring implementation of school nutrition program (Home Grown School Feeding Programme (HGSFP)) | 60 schools | Number of schools serving nutritious meals through the HGSFP, at tuck shops | Grain Relish Fuel | Termly | MOPSE & MOHCC
 |  | Establish and ensure maintenance of nutrition gardens at institutions | All hospitals, schools, correctional services facilities, waiting mothers shelters, old peoples’ homes, etc.) | Number of institutions with established nutrition gardens | Agriculture inputs | 2ND quarter | AGRITEX
 |  | Conduct support visits to institutions to ensure preparation of quality four-star meals | All institutions | Number of institutions serving nutritious 4 star meals | Fuel DSAs | Quarterly | MOHCC

## Slide 8
Key Result Area | Activity | Sub Activities | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 6 | Participate in food and nutrition security data collection, timely information dissemination, utilization and feedback | Participate in ZIMLAC urban and rural assessments | All sectors (Health, Agriculture, Social Welfare, Local Govt, local authorities, Education, Information, Women Affairs, Youth, ZIMSTAT, EMA, DDF, NAC, NGOs, and other stakeholders) | Number of sectors participating in data collection, analysis, reporting and timely information dissemination, utilization and feedback | Vehicle, Data collection tools, Computers DSAs | Annually (and as per rising need) | Local Govt
 |  | Conducting Provincial, and District Food and Nutrition Security committee meetings | All sectors | Number of sectors participating FNSC meetings | Refreshments | Quarterly (and as per rising need) | MOHCC AGRITEX Social Services Local Govt
KRA 7 | Train Ward Level FNSCS in Food Mitigation Strategy and the Work of FNSCs | Adoption of Multisectoral Community Based Model to reduce stunting (MSCBM) in all the remaining districts | Goromonzi and Marondera district | Number of WFNSC established |  |  | 
 |  | Establish Youth Business Units for the Centers and Youths | 6 | Number of Youth Business Units for the Centers and Youths established | G.O.Z | 12 months | Ministry of youth
 |  | Establishment of Value Chains at Training Centers | 6 | Number of Value Chains Established at Training Centers | G.O.Z | 12 months | Ministry of youth