## Slide 1: FNSC WORK PLAN JANUARY- DECEmber 2025
Mashonaland West
PROVINCE

## Slide 2
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 1 | Strengthen Provincial Food and Nutrition Security committee coordination | Provincial food and nutrition security committee quarterly meetings | Number of PFNSC meetings conducted. | Lunches and refreshments, projector, Stationery, printer and laptop | Quarterly | MOHCC -Nutrition
 | Conduct joint monitoring vists to food security and livelihoods projects | 4 | Proportion of Joint monitoring visits conducted | Vehicle Fuel DSAs | January- December | Min of Local Government

## Slide 3
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 2 | Farmers Trained | 531 800 | Number of farmers trained | Power Point Projectors Gazebos, Banners, Excellence/ Demonstration kits, Exhibits, Stationary, airtime/ Bundles and Traveling and Subsistence | 1 Jan 25 to 31 Dec 25 | AGRITEX
 | Maize Produced | 540 000 MT | Maize Produced | Promotional materials, airtime, stationary, airtime/ Bundles and Traveling and Subsistence | 1 Jan 25 to 31 Dec 25 | AGRITEX
 | Wheat Produced | 187 000 MT | Wheat Produced | Promotional materials, stationary, airtime/ Bundles and Traveling and Subsistence | 1 Jan 25 to 31 Dec 25 | AGRITEX
 | Crop, Livestock and Fisheries Assessment conducted | 2 | Number of crop and livestock assessments conducted | Stationary, airtime/ Bundles and Traveling and Subsistence | 1 Jan 25 to 31 Dec 25 | AGRITEX

## Slide 4
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 2 | Beef Production | 5% | Beef Produced | Promotional materials, airtime, stationary, airtime/ Bundles and Traveling and Subsistence | 1 Jan 25 to 31 Dec 25 | AGRITEX
 | Milk Production | 6M Litres | Milk Produced | Promotional materials, airtime, stationary, airtime/ Bundles and Traveling and Subsistence | 1 Jan 25 to 31 Dec 25 | AGRITEX
 | Fish Ponds Stocking | 56 | Number of fish ponds stocked | Fingerlings, Promotional materials, airtime, stationary, airtime/ Bundles and Traveling and Subsistence | 1 Jan 25 to 31 Dec 25 | AGRITEX
 | Dam Stocking | 20 | Number of dams stocked | Fingerlings, Promotional materials, airtime, stationary, airtime/ Bundles and Traveling and Subsistence | 1 Jan 25 to 31 Dec 25 | AGRITEX

## Slide 5
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 2 | Migratory Pest containment | 26 | Traps set | Traps, airtime/ Bundles and Traveling and Subsistence | 1 Jan 25 to 31 Dec 25 | AGRITEX
 | Hay bales production | 875 000 | Bales Produced | Bailing equipment and materials, airtime/ Bundles and Traveling and Subsistence | 1 Jan 25 to 31 Dec 25 | AGRITEX
 | Carcass grading | 100% | Carcases graded | Protective Clothing, grading materials, airtime/ Bundles and Traveling and Subsistence | 1 Jan 25 to 31 Dec 25 | AGRITEX
 | Sweet potato vines distribution | 100% | Vines Distributed | Promotional materials, stationary, airtime/ Bundles and Traveling and Subsistence | 1 Jan 25 to 31 Dec 25 | AGRITEX

## Slide 6
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Strengthening food deficit mitigation interventions to address food and nutrition security to vulnerable households | 100% of vulnerable households | Proportion of vulnerable households receiving support | Food hampers Fuel DSAs | Monthly | Department of Social Development, OPC and Local Government, MOHCC.
 | Vulnerable people accessing health services at health facilities and integrated outreach points | 100% of vulnerable households | Proportion of women, children, adolescents and senior citizens receiving health services. | Finances for provision of care and medicines | January - December | MOHCC, DSD
 | Provision of nutritious meals to learners | 100% of learners in school | Proprtion of learners receiving meals at school | Food provisions | January - December | MoPSE
KRA 3

## Slide 7
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Capacitation of health cadres on food inspection and monitoring of the code of marketing of breastmilk substitutes. | All public health officers in 7 districts | % coverage of health staff capacitated by district. | Food DSAs Fuel | 31 December 2025 | MOHCC-Environmental health
 | Engagement and coordination of sector ministries on food safety through the One health approach. | Law enforcement agents, policy markers, AREX, Vert. officers, and Public health officers (Collaboration or integration) | Proportion of ministries reached. | Refreshments | 31 March 2025. | MOHCC-Environmental health
 | Coordinate and monitor the training of food handlers in 7 districts. | 7 districts | Proportion of food handlers trained with approved certificates | Stationery, allowances and teaching aids | 31 December 2025 | MOHCC-Environmental health
 | Facilitate and monitor food inspection on trading and non trading premises to control food contamination and poisoning. | All food processing and and food outlets for public consumption | Proportion of food outlets inspected | Stationery | January to December | MOHCC-Environmental health
KRA 4

## Slide 8
Key Result Area` | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Monitor and support investigation of rumors and any public health incident. | 100% of public health incident reports investigated | Proportion of reported public health incidents investigated with reports | Fuel and allowance for staff | January- December | MOHCC-Environmental health
 | Monitor and ensure compliance to Public health act and SI 194 of 2024 (screening at ports of entry) to prevent food related risks | 4 | Number of surveillance reports from POE | Prosecution and detention forms | January - December | Ministry of health-environmental health and ZIMRA
 | Joint water quality monitoring visits | 4 | Number of visits done to assess water quality | fuel DSAs | January - December | RIDA, MoHCC
 | Monitor and support the training of households to build tippy taps (hand washing facilities) | 5000 households | Proportion of households with hygiene enabling facilities | Chigubhu gear Cement, builders | January to December | Health and Child Care, RIDA, Women Affairs
KRA 4

## Slide 9
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 5 | Capacitate district health teams on Integrated Management of Acute Malnutrition (IMAM) | 4 districts | Number of district health teams capacitated on IMAM Cure rate for acute malnutrition | IMAM guidelines, training material, DSA for trainers, vehicle and fuel | June 2025 | Ministry of Health, ACF/NAZ/IMC consortium
 | Improve quality of care in stabilization centres (SC) for IMAM | Refurbishment of 2 hospitals in Kariba and Mhondoro-Ngezi | Number of IMAM stabilization centres refurbished | Refurbishment materials and requirements( equipment, medicines and supplies, utensils etc) | October 2025 | Ministry of Health ACF/NAZ/IMC consortium
 | Strengthen capacity of community health workers to identify and refer malnutrition cases in the community | 4 districts | Number of capacitated on IMAM Number of children screened for malnutrition | Fuel Refreshments | March 2025 | Ministry of Health

## Slide 10
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Monitor and support care groups and Infant and Young Child Feeding support groups | 2 districts | Community mentorship reports | Fuel DSAs | Quarterly | MOHCC-Nutrition
 | Support districts on nutrition supply chain management | 7 districts | Nutrition commodities order fill rate | Fuel DSAs | Quarterly | MOHCC-Nutrition
 | Support and monitor the implementation of school nutrition program | 1 district (Makonde) | Number of adolescent children receiving meals at schools | Fuel DSAs | Quarterly | MOHCC-Nutrition
KRA 5

## Slide 11
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
 | Strengthen integrated outreach activities including nutrition activities (Screening for malnutrition, Vitamin A supplementation etc) for hard to reach areas | 7 districts providing integrated health care services to vulnerable households | Number of women, children, adolescents receiving health and nutrition services during integrated outreach activities. Number of integrated outreaches conducted. | Vehicles, DSAs for outreach teams, fuel | Quarterly | MOHCC
KRA 6 | Participate and support the collection, dissemination and utilization of food and nutrition security data | 7 districts | Number of PFNSC joint monitoring visits | Fuel DSAs | Quarterly | Local government
KRA 5

## Slide 12
Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
KRA 7 | Promote production, preservation and consumption of locally available nutritious foods | Conduct 7 cook out competitions and food fairs | Number of cook out competitions and food fairs conducted | Food items, utensils, prices, fuel for cooking, venues | January- December | Min of Tourism