Masvingo pFNSC

Masvingo Province  Work plan

| KRA | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Facilitate development of district response strategies to food and nutrition security priorities | 7 districts | Number of Wards with response strategies to food and nutrition security issues |  | March 2025 | MLGP,W,MOPSE,MOLAFWRD,,MOHCC MOPSLSW ,Local Authority ,ZIMSTAT |
|  | Conduct Monitoring Visits to Food and Nutrition projects | 3 projects per district | Proportion of Joint monitoring of FNS projects at district level | Fuel, Lunch Allowances Bond Paper Checklists | Quarterly |  |
| 2 | district Extension staff capacity building | 70 |  | Fuel Lunch Allowances Bond Paper IEC material |  | MOLAFWRD |
| 2 | Monitoring of Pest & Disease control (Scouting, surveillance, vaccinations, dipping) | All 7 districts | Number of animals vaccinated Quantity of dip chemicals supplied | Fuel Bond Paper Vaccines Dip Chemicals | ongoing | MOLAFWRD |
| 2 | Promote Climate SMART Agricultural Practices eg Pfumudza | 7 districts | Number of CSA techs adopted Proportion of HH adopting climate smart tech | Fuel Bond Paper Promotional IEC Materials | Ongoing | MOLAFWRD |
| 3 | Monitor Implementation of Nutrition Program |  | Number of schools implementing the HGSFP | Fuel Bond Paper Promotional IEC Materials Allowances |  | MOPSE,DSD,MOHCC |
| 3 | monitor the roll out of food mitigation program to food insecure population | 100% of food insecure households | Proportion of Vulnerable households receiving SP support | Fuel Bond Paper Promotional IEC Materials Allowances | Ongoing |  |
| 3 | Monitor districts Implement livelihood projects that use labour saving technologies | Gutu,Chivi ,Mwenezi | Proportion n of functional projects | Fuel Bond Paper Promotional IEC Materials Allowances | October | Women Affairs ,Social Services,ARDAS |
| 4 | Enforce compliance and certification of all locally produced and imported foods | 7 districts | Number of prosecutions done | Fuel Bond Paper Promotional IEC Materials Allowances | Ongoing | MOHCC, MOLAFWRD |
| 5 | Capacity strengthening of stakeholders in IYCF (health workers, caregivers, community leaders, etc) | 7 districts | Number of districts implementing SBCC (care groups, support groups) | Fuel Bond Paper Promotional IEC Materials Allowances | Ongoing | MOHCC Women Affairs |
| 5 | Strengthen health and nutrition programmes in institutions of care (schools, correctional services, waiting mother’s shelters shelters, old people’s homes, | 35 schools (5 per district) 3 correctional centers 2 old people’s homes. 4 waiting shelters(Gutu rural,Neshuro,Musiso mogenster. | Number of schools serving nutritious meals through the Home Grown School Feeding Programme, at tuck shops | Fuel Bond Paper Promotional IEC Materials Allowances | Quarterly | MOHCC,MOPSE,DSD Women Affairs |
| 6 | Participate in food and nutrition security data collection, timely information dissemination, utilization and feedback | ZIMLAC rural and Urban Assessment | Number of sectors participating in data collection, analysis, reporting and timely information dissemination, utilization and feedback | Fuel Bond Paper Allowances | On call | MLGP,W,MOPSE,MOLAFWRD,,MOHCC MOPSLSW ,Local Authority ,Partners,ZIMSTAT |
| 7 | Facilitate the development of Ward Food and Nutrition Security Committee | 5 districts (Chiredzi,Chivi,Gutu ,Zaka,Mwenezi | Number of functional WFNSCs |  | by Q3 q1,q2 |  |

Members present

| Name | sex | Organisation | contact number | email |
| --- | --- | --- | --- | --- |
| Madusise Marvellous | female | MOPSLSW(DSD) | 0771140500 | marvellousmadusise@gmail.com |
| Muyani Cephas | male | MoPSE Ministry of Primary and Secondary Education | 0772985607 | cmuyani@gmail.com |
| Mapanga Golden Mugove | male | MOPSLSW(DSD) | 0772245176 | gmmapanga@gmail.com |
| Hove roy | male | MLGPW | 0776202246 | localgovernmentmasvingod@gmail.com |
| Moyo Zanele | female | MOHCC Ministry of Health and Child Care | 0785072975 | zanmoyo1@gmail.com |
| Nesta Mashavira | male | Aquaculture Zimbabwe | 0783523115 | nestamashavira@gmail.com |
| Chidziya Pheobie | female | VET | 0715484462 | pheochidziya@gmail.com |
| Chaduka Sabina | female | ARDAS | 0775748660 | sbnchaduka@gmail.com |
| Joseph Mugaiwa | male | NANZ | 0772563043 | jmugaiwa@gmail.com |