## Slide 1: Mat South PFNSC Workplan

## Slide 2
KRA | Activity | Target | Process Indicator | Inputs | Timeline | Lead Agency
1 | Facilitate development of District response strategies to food and nutrition security priorities | 7 Districts | Number of Districts with response strategies to food and nutrition security issues | Fuel, Lunch Allowances Refreshments | March 2025 | Director Local Government Services, ARDAS, MOHCC, Social Services
1 | Conduct Monitoring Visits to Food and Nutrition projects | 50% | Proportion of Joint monitoring of FNS projects at District level | Fuel, Lunch Allowances Bond Paper Checklists | Quartely | Director Local Government , ARDAS, MOHCC Social Services, (Local Development Partner)

## Slide 3
KRA | Activity | Target | Process Indicator | Inputs | Timeline | Lead Agency
2 | Diversified Crop & livestock Inputs distribution | 5 000Ha Maize | Number of Ha planted | Fuel Bond Paper Input Packs | ongoing | ARDAS
2 | Pest & Disease control (Scouting, surveillance, vaccinations, dipping) | Cattle 1000000 (1kg) teak grease tins | Number of animals vaccinated Quantity of dip chemicals supplied | Fuel Bond Paper Vaccines Dip Chemicals | ongoing | ARDAS
2 | Promote Climate SMART Agricultural Practices eg Pfumudza | 500000 plots | Number plots targeted (90% adoption) Proportion of HH adopting climate smart tech | Fuel Bond Paper Promotional IEC Materials | Ongoing | ARDAS
3 | Promote Schools to implementing Home Grown School Feeding Programme | 513 Pri schools | Number of schools implementing the HGSFP | Fuel Bond Paper Promotional IEC Materials Allowances |  | MOPSE MOHCC SSD

## Slide 4
KRA | Activity | Target | Process Indicator | Inputs | Timeline | Lead Agency
3 | Providing school meals | 100% | Number of learners provided with one hot balanced school meal/school day | Fuel Bond Paper Promotional IEC Materials Allowances | Ongoing | MPOSE MOHCC
3 | Implement livelihood projects that use labour saving technologies | 50% | Proportion of farmer women accessing labour saving Technologies | Fuel Bond Paper Promotional IEC Materials Allowances | October | Women Affairs ,Social Services, ARDAS
4 | Enforce compliance and certification of all locally produced and imported foods | 100% | Compliance Number of violations observed | Fuel Bond Paper Promotional IEC Materials Allowances | Ongoing | MOHCC
4 | Train households to build tippy taps (hand washing facilities) | 80% | Proportion of households with hygiene enabling facilities | Fuel Bond Paper | Ongoing | MOHCC

## Slide 5
KRA | Activity | Target | Process Indicator | Inputs | Timeline | Lead Agency
3 | Rolling out food mitigation program to food insecure population | 343658 | Proportion of beneficiries receiving SP support | Fuel Bond Paper Promotional IEC Materials Allowances | Ongoing | 
3 | Implement livelihood projects that use labour saving technologies | 50% | Proportion of farmer women accessing labour saving Technologies | Fuel Bond Paper Promotional IEC Materials Allowances | October | Women Affairs ,Social Services, ARDAS
4 | Enforce compliance and certification of all locally produced and imported foods | 100% | Compliance Number of violations observed | Fuel Bond Paper Promotional IEC Materials Allowances | Ongoing | MOHCC
4 | Train households to build tippy taps (hand washing facilities) | 80% | Proportion of households with hygiene enabling facilities | Fuel Bond Paper | Ongoing | MOHCC

## Slide 6
KRA | Activity | Target | Process Indicator | Inputs | Timeline | Lead Agency
5 | Capacity strengthening of stakeholders in IYCF (health workers, caregivers, community leaders, etc) | 145 wards | Number of wards implementing SBCC (care groups, support groups, PHCs, etc) | Fuel Bond Paper Promotional IEC Materials Allowances | Ongoing | MOHCC CTDO WV NAZ Women Affairs
5 | Strengthen health and nutrition programmes in institutions of care (schools, correctional services, waiting mothers shelters, old peoples homes, | 80% institution | Number of schools serving nutritious meals through the Home Grown School Feeding Programme, at tuck shops | Fuel Bond Paper Promotional IEC Materials Allowances | Quarterly | MOHCC MPOSE Women Affairs
6 | Participate in food and nutrition security data collection, timely information dissemination, utilisation and feedback | At least 5 sectors | Number of sectors participating in data collection, analysis, reporting and timely information dissemination, utilisation and feedback | Fuel Bond Paper Allowances | Oncall | Director Local Government Services ARDAS
7 | Train Ward Level FNSCS in Food Mitigation Strategy and the Work of FNSCs | 145 | Number of WFNSC established | Fuel, Bond Paper IEC Materials , Training Materials Allowances | August | Director Local Government Services Social Services