MATABELALAND NORTH

PROVINCIAL FOOD AND NUTRITION SECURITY COMMITTEE (PFNSC)

2025 ANNUAL WORKPLAN

1.0 Policy Analysis and Advice

| KRA | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1-day PFNSC monitoring visit to Lupane with 10 members of the PFNSC | 1 monitoring visit | Number of provincial monitoring visits | Fuel, Lunches | April/May | Amalima Loko, |
| 1 | PFNSC monitoring and field visits | 2 visits in 4 wards in Tsholotsho | Proportion of joint monitoring of FNS projects at ward level | Fuel, Lunch Allowances | Bi annually | CTDO |
| 1 | Monitoring visit | 1 monitoring visit | Number of monitoring visits | Lunch allowance | June/July | SRP/NAZ |
| 1 | Quarterly review and coordination meetings | 4 | Number of meetings conducted | Allowances, stationery ,fuel | Q1-Q4 | Agritex ,DSD,MOHCC |

2.0 Nutrition Sensitive Agriculture

| KRA | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency/Supporting Agencies |
| --- | --- | --- | --- | --- | --- | --- |
| 2 | Training of extension officers on silage making ,bailing of fodders crops and urea stova treatment | 474 extension officers | Number of extension officers trained | Urea fertilizer, Damp liners, Molasses Threads, Crates | 1st and 2nd Quarter | Agritex, |
| 2 | Training farmers on Climate Smart Agricultural Practises eg Pfumvudza | 230000 | Number of farmers trained | Fuel, Flip boards and charts, mighty markers | 2nd to 3rd Quarter | Agritex |
| 2 | To have field days, shows And ZITF | 14 field days 8shows 1 ZITF | Number of field days held Number of shows held Host ZITF |  | 1st to 3rd Quarter | Agritex ,GVT Departments and NGOS |
| 2 | Diversified crop and livestock input distribution | 230000 | Number of farmers receiving inputs | Transport, register’s, Airtime | 1st and 4th Quarter | Agritex |
| 2 | Pest and disease control scouting in field crops | 230000 | Number of farmers trained | Airtime, flip charts and flip board, mighty markers | 1st and 4th Quarter | Agritex |
| 2 | Winter wheat planting | 1000ha | Number of hectares planted | Registers, Transport,airtme | 2nd Quarter | Agritex |
| 2 | -Train farmers on tree nursery establishment and agroforestry techniques -Establish nurseries in community nutrition gardens -Distribute 2 grafted fruit trees per household in Tsholotsho(Ward 1,5,6,10,17,18,21) | CTDO: 10 Nutrition gardens 175 households(grafted trees | Number of farmers trained Number of nurseries established Number of farmers practising agroforestry | Potting material, seeds, IEC material, Fuel, Allowances | Q1-Q4 | Forestry Commission, Agritex ,EMA ,CTDO |
| 2 | Improved breed chickens (sasso) pass-on within FFS and Care-groups in Tsholotsho | 7 wards- 35 FFS, 96CG. | Quantity of inputs distributed, number of HH receiving. | Fuel, sasso chicks, | Ongoing | CTDO, ARDAS, |
| 2 | Improved goat breed distribution and pass-on-Tsholotsho | 2 wards | Quantity of inputs distributed number of HH receiving. | Transportation truck, | March 2025 | CTDO, ARDAS, VET |
| 2 | Training of young farmers on dairy production | 250 | Number of young farmers trained |  | Q1 | Youth,ILO, Agritex, |
| 2 | Training lead farmers on healthy harvest and agro ecological gardening | 100 | Number of lead farmers trained | Training material, Lunch | Q2 and Q3 | SRP/NAZ |
| 2 | Support farmers at demo sites to reinforce skills and trouble shoot | 55 | Number of demo sites supported | Seeds | Ongoing | SRP/NAZ |
| 2 | Support communities in the design and establishment of resilient design structures to increase water and moisture retention and enhance fertility | 25 | Number of Lead farmers trained | Training material & lunch | Q1 ; Q3 & Q4 | SRP/ORAP/Agritex |
| 2 | Support communities in the design and establishment of resilient design structures to increase water and moisture retention and enhance fertility | 200 | Number of farmers trained | Training material & lunch | Q3 & Q4 | SRP/ORAP/Agritex |
| 2 | Train female smallholder farmers to preserve and produce community-preferred indigenous crops and plants in field and homestead gardens (Permagardens) | 90 | Number of farmers trained | Training material & lunch | Q3 & Q4 | SRP/ORAP/Agritex |
| 2 | Train farmers on knowledge systems for sustainable production, extraction, and use of indigenous plants and NTFP in Tsholotsho | 200 | Number of farmers trained | Training material & lunch | Q3 & Q4 | SRP/ORAP/Agritex |

3.0 Nutrition Sensitive Social Protection

| KRA | ACTIVITY | TARGET | PROCESS INDICATOR | RESOURCES | TIMELINE | LEAD AGENCY |
| --- | --- | --- | --- | --- | --- | --- |
| 3 | Train cluster Heads, Schools Inspectors, DSIs on Schools to implement Home Grown School Feeding Programme | 632 Primary schools 217 Secondary schools | Number of Heads, Schools Inspectors, DSIs trained Number of schools implementing HGSFP | Fuel Bond paper Promotional IEC materials Allowances | Q1-Q4 | MOPSE |
| 3 | Facilitate the formation of School Health clubs | 849 health clubs | Number of school health clubs | Fuel Participatory Health and Hygiene Education (PHHE) tools Bond paper Promotional IEC materials Allowances | Q1-Q4 | MOPSE, MOHCC, Camfed ZIMTTECH |
| 3 | Facilitate the establishment of SBUs( fish ponds, livestock, trees, school Nutrition Gardens) | 849 school gardens | -Number of schools with: a. School Nutrition Gardens b. fish ponds c. fruit and leguminous trees d. livestock and poultry | Garden Inputs(seeds , perimeter fence) Pesticides, Garden tools, PPE | Q1-Q4 | MOPSE, AGRITEX ,Forestry Commission ,EMA ,Local Authorities, Zim Parks, LSU,MOHCC,RIDA,ZINWA,DOI |
| 3 | Establish livelihood support for the vulnerable | 3 | Number of projects established | Garden inputs | Q1-Q4 | DSD, MLG, RIDA, AGRITEX, LA |
| 3 | Payment of school fees, provision ,uniforms food packs and stationery for OVCs | 109 500 | Number of OVCs reached |  | Q1- Q4 | DSD, MOPSE, ZIMTTECH, Higher Life, Camfed, ORAP |
| 3 | Facilitate capacitation of CPCs,DDRCs, | 7 Districts | Number of capacitated districts |  | Q1 | DSD,MLG,MOPSE,LA |
| 3 | Facilitate the Implementation of the HGSFP | 215868 learners | Number of learners receiving one hot balanced meal per school day | Fuel Bond paper Promotional IEC materials Allowances | Q1-Q4 | MOPSE |
| 3 | Distribution of food and NFI vouchers | 7704-Tsholotsho 7400-Binga 524713(Province) | Number of people receiving food baskets | Food Basket($19.50) | Q1 | DSD, ACF |
|  |  | 28295 | Number of people receiving cash for cereal |  |  |  |
| 3 | Establish projects for persons with disabilities | 3 projects per district | Number of projects established | CDCs | Q1-Q4 | DSD, ARDAS, Women Affairs, Youths, |

4.0 Nutrition Sensitive Food Safety and Standards

| Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- |
| 4 | enforce compliance and certification of all locally produced and imported foods | 95% | Proportion of compliance reported | Fuel, Bond paper, Promotional I.E.C material, allowances | Q1-Q4 | MOHCC |
| 4 | Capacity strengthening of Health Clubs on PHHE | 2000 | Number of people trained in PHHE Number of households with functional hygiene enabling facilities | Fuel, Bond paper, Allowances Training material | Q1-Q4 | MOHCC, Amalima Loko |
| 4 | Increase awareness on household hygiene, sanitation and waste management amongst the communities through use of participatory approaches | 10 000 people(WASH SBCC) 700 Clean-up campaign 3 WASH Commemoration | Number of population reached with WASH behaviour change campaigns. Number of clean ups conducted Number of WASH significant days commemorated Number of groups engaged in waste recycling | Bond paper, allowances | Q1-Q4 | MOHCC , Amalima Loko ,CTDO ,Local Authorities ,EMA ,National Housing ,RIDA ,ZINWA |
| 4 | Construction of self-supply latrine building to improve sanitation coverage | 400builders 1500 latrines | Number of latrine builders trained Number of latrines constructed | Training materials, trained latrine builders | Q1-Q4 | MOHCC, Amalima Loko ,CTDO , Local Authorities |
| 4 | Increase capacity on drinking water testing | 1500 water sources sampled | Number of water sources tested | Lab consumables | Ongoing | MOHCC, CARITAS |
| 4 | Conduct ambient water sampling | 288 samples | Number of samples tested | Sampling bottles ,T&S ,Fuel, PPE, Freighting | Monthly | EMA, ZRP, ZimParks |
| 4 | Conduct ecosystems inspections: Stream bank cultivation enforcement | 405 inspections | Number of inspections done | Fuel, Allowances PPE, Stationery, | Q1-Q4 | EMA, Local Authorities, ZRP, ZimParks |
| 4 | Borehole drilling | 18 boreholes | Number of boreholes | Drilling consumables, PPE, Allowances | Q2-Q4 | RIDA, CTDO, ZINWA, Local Authority, MOHCC |

5.0 Nutrition Security

| Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- |
| 5 | Quarterly Nutrition Briefs | 4 | Number of Nutrition Briefs | Fuel Bond paper Allowances Conference Facility | Quarterly | MOHCC |
| 5 | Supplement at least 60% of children with Vitamin A | 60% | Proportion of Children receiving Vitamin A | Vitamin A Capsules M&E tools | Monthly | MOHCC,IMC |
| 5 | Track growth and development of at least 50% of children monthly | 50% | Proportion of children weighed | Salter scales VHWs Stationery Incentives | Monthly | MOHCC,IMC |
| 5 | Launch awareness campaign through local radio stations ,bulk messages and community leadership | 1 round | Number of districts participating in the awareness campaigns Number of bulk messages sent | Fuel , Vehicles, IEC materials, Allowances | 1st Quarter | MOHCC,CTDO, Ministry of Information, Local Government |
| 5 | VHWs refresher training on Active screening, Growth monitoring and Vitamin A, Caregroups, IYCF, IMNCI, in the 6 Emergency districts (Binga ,Hwange ,Tsholotsho ,Umguza, Bubi,Nkayi) | 11600 | Number of VHWs capacitated | Fuel Vehicle Scales Stationery | 2nd Quarter | MOHCC, IMC , CTDO |
| 5 | Training of Nurses IMAM, IMNCI, IYCF e in Tsholotsho and Binga | 40 | Number of nurses trained | Training materials | Q1-Q3 | MOHCC, IMC, |
| 5 | Equipping of Stabilisation Centres in Binga and Tsholotsho | 2 | Number of stabilisation centres equipped | Fuel, Mother Baby Scales, Stationery | Q1-Q3 | MOHCC, IMC |
| 5 | Conduct outreach services in Hard to reach areas in Binga and Tsholotsho | 100 outreaches | Number of outreaches done | Essential Medicines, Supplies, Visibility materials, Doctor, Allowances, Fuel,Ambulances | Q1-Q3 | MOHCC, IMC |
| 5 | Conduct breastfeeding awareness campaign in all the districts during the World Breastfeeding week. | 7 | Number of districts conducting awareness campaigns | IEC Materials Fuel Vehicles Allowances | August | MOHCC, CTDO, |
| 5 | Iron folic acid(IFA) supplementation to in school adolescents in (Binga and Hwange | 48102 | Number of adolescents receiving IFA | IFA tablets Hb machines Logistical Support ICT(smart phones) for reporting purposes | 1st and 2nd term | MOHCC/MOPSE |
| 5 | Blanket supplementary feeding program activities (BSFP) | 12,000 P&LW 24,000 6-23 months children | Number of PLWs and children between 6-23 months receiving rations | CSB plus, vegetable oil | December (monthly distributions through clinics) | MOHCC, Amalima Loko |
| 5 | Care group trainings- Monitor coach and mentor the lead mothers on care group activities with a focus on the health and nutrition priority behaviors | 400 new lead mothers 3,000 Lead Mothers 100- lead mothers | Number of new lead mothers trained Number of lead mothers trained on care group activities Number of lead mothers supported in facilitating care groups | Training materials | December | MOHCC, Amalima Loko, CTDO,SRP/NAZ |
| 5 | Supporting mothers/caregivers in care group activities with a focus on the health and nutrition priority behaviors | 15,000 | Number of mothers/caregivers participating in care group activities | Care group sessions | December | MOHCC, Amalima Loko, CTDO |
| 5 | Cooking demos conducted with mothers/caregivers to promote nutritious locally available food. | 1000 | Number of cooking demos conducted | Recipe guides | December | MOHCC, Amalima Loko, CTDO, Women Affairs |
| 5 | Coaching and mentoring of Male champions on nutrition activities and supporting male peers. | 300 male champions 3,000 male peers | Number of Male Champions coached and mentored Number of male peers supported | Coaches and Mentors | December | Women Affairs,Amalima Loko,MOHCC, PADARE, |
| 5 | Establishment of Micro-gardens | 4,000 | Number of Micro-gardens established by mothers/caregivers | Healthy harvest trainings | December | Agritex, MOHCC, Amalima Loko, DOI, EMA, Local Authorities |
| 5 | Conduct Health and Nutrition Community dialogues at village level | 620 community dialogues | Number of Health and Nutrition Community dialogues conducted | Brief Dialogue guide (dialogues are conducted by village health workers) | December | Local Government, MOHCC, Amalima Loko |
| 5 | Cooking demos conducted with mothers/caregivers to promote nutritious locally available food. | 1000 | Number of cooking demos conducted | Recipe guides | December | MOHCC, Amalima Loko, CTDO, Women Affairs |
| 5 | Coaching and mentoring of Male champions on nutrition activities and supporting male peers. | 300 male champions 3,000 male peers | Number of Male Champions coached and mentored Number of male peers supported | Coaches and Mentors | December | Women Affairs,Amalima Loko,MOHCC, PADARE, |

6.0  Food and Nutrition Information Assessment, Analysis and Early Warning

| KRA | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- |
| 6 | Crop and livestock data collection | 3 (1st ,2nd and 3rd round) | Number of assessments done | Fuel,Allowances Airtime,Smart Phones, | 1st and 2nd Quarter | ZIMSTAT, Agritex |
| 6 | Participation in the national food and nutrition security data collection(ZMLAC) | 2 (Urban and Rural) | Number of assessments done | Fuel,Allowances Airtime,Smart Phones, | 1st and 2nd Quarter | OPC,DSD, LA,MOHCC, Agritex,MLG, Partners |
| 6 | ZMLAC information dissemination | 2 (Urban and Rural Assessment) | Number of dissemination meetings conducted | Fuel,Allowances | 2nd and 3rd Quarter | OPC,DSD, LA,MOHCC, Agritex,MLG, Partners,Information |
| 6 | Centred Approach to beneficiaries assessments, feedback and learning platforms | 5 | Number of feedback session conducted |  | Q1-Q4 | MOHCC,DSD, IMC, ACF, Musasa |
| 6 | Nutrition gap analysis | 1 | Number of assessments done |  | Q1 and Q2 | SRP/NAZ |
| 6 | 4 assessments (crops, livestock, NTFPs & social enterprises) | 4 | Number of assessments (Resource mapping) | Consultant fees | Q1 & Q2 | SRP/ORAP/Agritex |
| 6 | Conduct Research on indigenous plants & Crops | 1 | Number of researches (Resource mapping) | Consultant fees | Q1 &Q2 | SRP/ORAP/Agritex |

7.0 Enhancing and Strengthening Capacities for Food and Nutrition Security

| Key Result Area | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- |
| 7 | Training of PFNSC on FNSC and MCBM,ECD | 35 | Number of member trained | Conference, Allowances | Q2 | OPC,Agritex, DSD,MOHCC,LA |
| 7 | Training of DFNSCs on ECD, (Bubi,Lupane,Umguza,Nkayi) | 4 | Number of districts trained | Conference, Allowances,Fuel | Q3 | OPC,Agritex, DSD,MOHCC,MLG |
| 7 | Refresher training for WFNSCs in Tsholotsho | 7 Committees | Number of WFNSCs trained | Stationery,refreshments Lunch allowances | Q1 | OPC,Agritex, DSD,MOHCC,MLG,CTDO |
| 7 | DRR campaigns in Tsholotsho | 7 campaigns | Number of campaigns Number of wards reached | Refreshments, Lunch allowances, Fuel | Q2 | CTDO,MLG, EMA, Forestry,LA,CPU Committee |
| 7 | Workshops to establish and promote ISALS | 37 ISAL groups | Proportion of HH participating in ISALs Number of groups trained. | Refreshments, stationery, lunch allowances | Q1-Q4 | CTDO, Women Affairs. |
| 7 | Establish business hubs | 1 seed bank 3 group level business hubs | Proportion of HH participating in income generation projects | Incubator, oil pressing machine, peanut butter machine, thresher, | Q1 2025 | CTDO, Women Affairs |
| 7 | Construction of low cost demo solar driers | 14 | Number of solar driers constructed | Materials for demo solar drier construction | Q1 2025 | CTDO |
| 7 | Low cost solar driers for early adopters (farmer to contribute some of the materials) | 200 | Number of early adopters | Part materials for solar driers | Ongoing | CTDO, ARDAS |
| 7 | Workshops to establish and promote ISALS | 37 ISAL groups | Proportion of HH participating in ISALs Number of groups trained. | Refreshments, stationery, lunch allowances | Q1-Q4 | CTDO, Women Affairs. |
| 7 | Cookout competition | 1 per each district 1 Provincial event | Number of cookout competitions held | Competitors | Q 1-Q2 | Women Affairs |
| 7 | Trainings of women and community members in technical and social skills | 16000 | Number of women trained Number of community members trained | Trainers | Q1- Q 4 | Women Affairs |
| 7 | Funding of women and community projects through WDF and ZCDF | 15 projects | Number of funded projects | WDF ZCDF | Q1-Q4 | Women Affairs |