## Slide 1: Midlands Province FNC Workplan

## Slide 2
KRA | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
1 | Facilitate development of Ward FNC C0MITTEES | 100Wards | Number of WARD FNC COMITTEES Established | Fuel, Lunch Allowances | 1st Quarter | LOCAL Government ,OPC,ARDAS,MOHCC, Social Services,Women Affairs, Youth ,development Partners
2 | Train district agronomists on wheat production. | 8 gronomist | Number of district agronomists trained | Fuel, Lunch Allowances bond Paper for fact sheets | April 2025(2nd quarter) | ARDAS,Seed houses
3 | Train farmers on (Climate resilient Agriculture, Impact of climate change, Climate resilient practices) | 350000 farmers | Number staff and farmers trained | Fuel,lunch allowance,bond paper for fact sheets | ongoing | MLAFWRD
4 | Train district farmers on climate smart agriculture technology ie Pfumvudza/Intwasa concept | 350000 farmers | Number of Farmers trained | Fuel, lunch allowance, bond Paper for fact sheets, input packages | ongoing | MLAFWRD
5 | Aquaculture production | 8 districts | Number of districts staff and farmers trained trained | Fuel, T&S , Stationery, material for pond construction , | 3rd Quarter | ARDAS,Development partners
6 | Training on livestock drought mitigation strategies | 8 districts | Number of farmers trained | Fuel , stationery , T&S | 2nd Quarter | ARDAs,Developmental Partners
7 | Establishing Ward Drought Mitigation centers | 100 | Number of Drought mitigation centers established | Fuel, T&S , | On going process | ZINWA ,VET, LOCAL Government ,OPC,ARDAS,MOHCC ARDA
8 | Establishing Business Units | 2500 | Number of Business Units established | Fuel ,T&S | On going process | ZINWA,VET,ARDA, LOCAL Government ,OPC,ARDAS,MOHCC ,MINISTRY OF EDUCATION, WOMEN AFFAIRS ,YOUTH

## Slide 3
KRA | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
10 | Training on nursery production | 8 districts | Number of farmers trained | Fuel, Stationery , T&S | On going process | ARDAS, FORESTRY , EMA
11 | Food Fairs Competition | 8 districts | Number of competition done | Fuel, prices , T&S | On going process | ARDAS,LOCAL GVNT,ARDA, MIN HEALTH, SCHOOLS , WOMEN AFFAIRS ,YOUTH
112 | Conduct Monitoring Visits to Food and Nutrition projects | 80% | Reports produced | Fuel, Lunch Allowances Bond Paper Checklists | Quartely | DDC, ARDAS, MOHCC Social Services, (Local Development Partner)
8 | Establishing Farmer Field Schools | 660 | Number of Farmer Field Schools established | Fuel ,T&S | On going process | ZINWA,VET,ARDA, LOCAL Government ,OPC,ARDAS,MOHCC ,MINISTRY OF EDUCATION, WOMEN AFFAIRS ,YOUTH ,Development Partners
9 | Training on horticulture production (GAPS) | 8 districts | Number of staff members and farmers trained | Fuel, T&S, Stationery | On going process | ARDAS, ARDA, AMA
10 | Participate in food and nutrition security data collection, timely information dissemination, utilisation and feedback | 8 Districts | REPORTS PRODUCED | Fuel Bond Paper Allowances | Oncall | LOCAL Government ,OPC,ARDAS,MOHCC ,MINISTRY OF EDUCATION, WOMEN AFFAIRS ,YOUTH ,Development Partners ,SOCIAL SERVICE
11 | Carry out monthly and quarterly provincial FNC meetings. | 12 | Reports Produced | Lunch Allowances | Monthly/QUARTERLY | LOCAL Government ,OPC,ARDAS,MOHCC ,MINISTRY OF EDUCATION, WOMEN AFFAIRS ,YOUTH ,Development Partners ,SOCIAL SERVICE

## Slide 4
KRA | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
12 | Training of health workers on IMAM | 240 health workers in 8 Districts | Number of health workers trained on IMAM | DSA for 240 participants @120/day for 3 days= USD 86 400 Conference for 240 ppl @30/day/person =USD 21600 Bus fare for 240 ppl @10/person =USD 2400 Stationery – USD 100 | 3rd Quarter | MOHCC, UNICEF, WHO, NAZ
13 | Curing of malnourished cases | 78% cure rate across the province | Proportion of malnourished cases successfully cured admitted in the IMAM program | RUTF, F75, F100, RESOMAL | Quarterly | MOHCC, UNICEF, WHO
14 | Vitamin A supplementation | 85% coverage | Proportion of children supplemented with vitamin A | Vitamin A supplements | Bi-annually | MOHCC, UNICEF, WHO
15 | Implementation of the School Nutrition Program | 120 schools | Number of schools implementing the school nutrition program | Iron Folate Supplements Fuel – 400L @1.7/L = USD680 | Quarterly | MOHCC, MOPSE, UNICEF

## Slide 5
KRA | Activity | Target | Process Indicator | Resources | Timeline | Lead Agency
16 | Develop new Irrigation Schemes | 190Ha | Functional Irrigation Area | Project Budget: US$ 2 086 460.89 | Ongoing | OPC; MLAFWRD, LOCAL GVT; CCMT; POWER COMPANIES; DEPT OF MINES; S.WELFARE; PARTNERS; W.AFFAIRS; Dept of Youth; Min of Health , Communities; etc
17 | Irrigation Area Rehabilitated | 55Ha | Functional Area Maintained | Project Budget: US$200 000.00 | Quarterly | REFER ABOVE
18 | Irrigation Schemes Maintained | 4000HA | Maintained functional Irrigation area | Diesel 5000liters; vehicles; DSA | Quarterly | See above
19 | Planned New Project | 12No | Design Reports | Diesel 800liters | Ongoing | See above