BULAWAYO METROPOLITAN PROVINCE PROVINCIAL FOOD AND NUTRITION SECURITY COMMITTEE WORKPLAN TEMPLATE 2025

| ORGANISATION/ DEPARTMENT | KRA | ACTIVITY | TARGET | PROCESS INDICATOR/S | RESOURCES | TIMELINE | LEAD AGENCY |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DSD | 1. social protection | Cash transfer | 11500 beneficiaries | Number of beneficiaries | Stationery Funding | Jan-Dec 2025 | Department of Social Development(DSD) |
|  | 2. Sustainable Livelihood projects(SLP) | Livelihood projects/income generation | 2 | Number of projects established | Stationery Fuel Funding | Jan-Dec 2025 | Department of Social Development(DSD) |
|  | 3.Food distribution | Distribution of food provisions to elderly, children's and persons with disability institutions | 22 institutions | Food provisions supplied to the institutions | Fuel Food | Jan-Dec 2025 | Department of Social Development(DSD) |
|  | 4. Grants payment | Monthly disbursements of grants to institutions on monthly basis | 15 institutions | Total Institutions applying for grants | Stationery Funding | Jan-Dec 2025 | Department of Social Development(DSD) |
|  | 5. Monitoring & Evaluation | Visits to institutions implementing food & security activities |  | Total institutions/sites visited Visits reports | Stationery Fuel | Jan-Dec 2025 | Agriculture Ministry |
| HOCIC | Agriculture and Food Security | Farmer capacity building | 80 Households | Number of farmers trained Number of farmers with increased knowledge | Stationery Meals Vehicles Facilitation fees | 5 days: January | MLAFWRD |
|  |  | Training of schools and Establishment of climate change clubs | 7 Schools | Number of schools trained Number of climate change clubs established Climate change activism | Stationery Refreshments Vehicles | February | MOPSE |
|  |  | Monitoring of projects in schools established under the “Promotion of Agriculture in Schools concept | 1 visit in February | Number of monitoring visits conducted | Allowances Vehicle | February | MOPSE |
|  |  | Borehole drilling, capacity testing and solarisation | 1 borehole drilled (Mpopoma ward 9) | Number of boreholes drilled and equipped with solar | Rig Solar equipment | February (Subject to change) | MLAFWRD |
|  |  | Piped water scheme establishment | 1 piped water scheme developed (Mpopoma ward 9) | Number of households with increased access to clean domestic water | Plumbing equipment | February (Subject to change) | HOCIC |
|  |  | Establishment of gardens integrated with poultry and rabbits | 2 projects established (Nkulumane ward 23 and Mpopoma ward 9) | Number of gardens established Number of rabbits stocked Number of chickens stocked Increase in income Diversification of meals | Garden implements Vehicle Poultry inputs Rabbits inputs | February (Subject to change) | MLAFWRD |
|  |  | Establishment of a rabbits project | 30 rabbits stocked 1 project established at Ingutsheni Central Hospital in February | Number of rabbits projects established Number of rabbits reared | Building materials Rabbit cages Feed Weaners Breeders Vaccines | February (Subject to change) | MLAFWRD |
|  |  | Monitoring of projects in Ingutsheni Central Hospital and Ekuphumuleni Geriatric Nursing Home | 6 Bi-monthly visits conducted | Number of bi-monthly monitoring visits conducted | Vehicle Allowances | February - December | MLAFWRD |
| MOPSE | School feeding program | Feeding of all learners in all Bulawayo Primary and secondary schools excluding private school | Feeding leaners from ECD to ‘A’ Level | Feeding leaners 5 days a week. | Vegetables and maize | Jan- March 2025 | MOPSE, DSD |
|  | Nutrition garden | All schools to have nutrition garden with different types of vegetable -Grow maize | Vegetables for each season -Grow maize throughout the year for sell and for feeding learners | Growing different types of vegetables and maize by all primary and secondary schools | Vegetables and maize | Jan- March 2025 | MOPSE, DSD |
|  | Poultry farming | All primary and secondary schools to do either keeping, chicken keeping (broilers/ layers/road runners) | All schools to venture in either or all (rabbit, broilers, layers and road runners chicken) | For feeding learners -for selling the products to sustain school feeding program |  | Jan- March 2025 | MOPSE, DSD |
| ORAP | Social Protection | To distribute cash to the registered food insecure beneficiaries | 6000 beneficiaries in 3 Wards (9,18,28) | Number of beneficiaries receiving cash every month | Cash | On going | ORAP |
|  |  | To conduct monthly pre-disbursement meetings | 3 Wards | Number of beneficiaries attending these meetings | Lunch allowances vehicles | On going | ORAP |
|  |  | To conduct verifications to check on inclusion and exclusion errors | 3 wards | Number of inclusion and exclusion errors captured | vehicles | On going | ORAP |
|  | Social Protection | Conduct monthly cash out monitoring | 1114 households | Number of complaints and feedback received | Vehicles Helpdesk books | On going | ORAP |
|  |  | To conduct stakeholder review and feedback meetings | 4 | Number exit meetings conducted | Lunches Cash Meetings venue | March 2025 | ORAP |
|  |  | Training of community led groups to respond swiftly to community level crisis. | 100 individuals | Number of people trained on community led response | Cash Food Meeting venue | March 2025 | ORAP |
|  |  | To conduct markets Assessments | 10 shops | Number of shops monitored every month | Tablets Vehicle | On going | ORAP |
|  |  | To conduct Post Distribution Monitoring (PDM) | 8 | PDM reports produced | Tablets Data collectors cash | On going | ORAP |
| MINISTRY OF YOUTH , EMPOWERMENT , DEVELOPMENT AND VOCATIONAL TRAINING | Youth empowerment and development | Training in vocational skills (like carpentry, agriculture, hairdressing etc.) - Enrolment registers - Graduations | 2000 | No. of students enrolled -No. of students graduating |  | Ongoing | MYEDVT |
|  |  | Training in entrepreneurial skills (marketing, networking, value addition, company registration, financial literacy Workshops -Seminars - trainings | 10200 | No. of youth attending trainings |  | Ongoing | MYEDVT |
| MOHCC |  | Utilization of hospital land | . 40% | Number of functional gardens | Tools , fuel , food for nutritional gardens | Ongoing | MOHCC |
|  |  | Joint support collaboration to support community nutrition and hospital based nutrition interventions |  | Number of functional care groups Number of communities/ hospitals with nutritional gardens |  | Ongoing | MOHCC |
|  |  | Integration of nutrition in child, maternal and adolescent health services |  | number of people reached |  | Ongoing | MOHCC |
|  |  | Growth monitoring and promotion. Screening for NCDs l(diabetes ,obesity. | 50% | Coverage of micronutrients | Anthro equipment and glucometers | Ongoing | MOHCC |
|  |  | Track growth of children monthly IMAM |  | Number of children recorded for growth monitoring and promotion. |  | Ongoing | MOHCC |
|  |  | Promotion of good feeding and appropriate nutrition practices eg Breast feeding (week)awareness |  | Number of children with malnutrition. |  | Ongoing | MOHCC |
|  |  | Vit A Supplementation | 80% | Number of children supplemented with vitamin A. |  | Ongoing | MOHCC |
|  |  | Iron and Folic Acid supplementation in schools |  | Number of adolescents supplemented with IFA |  | Ongoing | MOHCC |
|  |  | Reach adolescents in school with Nutrition messages | 70 % | Number of schools were nutrition information has been disseminated |  | Ongoing | MOHCC |
| SNV | Scaling up Youth Employment in Agriculture ( Opportunities for Youth Employment) | Training of youth (life, financial, business & leadership) by selected LSPs and other implementing partners | At least 420 youth complete the basic life, financial and business skills training courses. | Private sector firms and value chain actors provide opportunities for young men and women as suppliers, service providers, retailers or employees thereby developing their youth inclusive business |  | Ongoing | SNV |
|  |  | Youth establish or are integrated into Youth Savings and Lending groups (YSALs) as a basis for Building a savings culture, credit management and financial discipline | At least 230 youth are involved in YSLs and are generating basic start-up capital for business investment and improve their financial skills | Number of youth with new / improved (self-) employment because of project initiatives. |  | Ongoing | SNV |
|  |  | Support Curriculum innovative adaptation by interested training providers to provide market relevant and climate smart technical training curriculum for youth | 51% of phase 2 OYE youth supported by the project accessing loans through YSL, private sector M/FI and Government. |  |  | Ongoing | SNV |
|  |  | Youth receive technical training and/or undergo apprenticeship and attachment for on-the-job training, experience and exposure in Horticulture/ Green Jobs/ Small livestock (Rabbitry/ Poultry) among other value chains. | At least 320 youth complete technical skills training courses in Horticulture/ Green Jobs/ Small livestock (Rabbitry/ Poultry) among other value chains. |  |  | Ongoing | SNV |
|  |  | Market partners and training providers identified and engaged | At least 200 youth coached and/or mentored (by OYE champions, LSPs, other |  |  | Ongoing | SNV |
|  |  | Youths provided with access to information, networks, platforms, services, and opportunities relevant to their value chain interest and entrepreneurial journey | 25 New Youth-led enterprises (YLEs) established and enter value chains identified |  |  | Ongoing | SNV |
|  |  | Youth are exposed to markets through learning visits, Youth Entrepreneurship Fairs/Exhibitions/Business Sharing | 10 Graduated youth-led enterprises have improved access to products and services related to markets, inputs, and extension. |  |  | Ongoing | SNV |
|  |  | Youth supported to develop viable business models related to identified opportunities | 25 business arrangements between private sector firms and youth led enterprises developed |  |  | Ongoing | SNV |
|  |  | Business plans developed with defined targets and investments for youth employment | 25 youth reporting increased access to resources such as Land, employment opportunities, and financial services |  |  | Ongoing | SNV |
|  |  | Establish linkages with appropriate markets, including export markets | 1 localized policy forums convened with active youth participation |  |  | Ongoing | SNV |
|  |  | Opportunities created for learning and interaction with market actors and mentors |  |  |  | Ongoing | SNV |
|  |  | strategic engagement with private sector |  |  |  | Ongoing | SNV |
|  |  | Meetings and negotiations organized between youths and companies |  |  |  | Ongoing | SNV |
|  |  | Conduct Community Gender Assessments and barrier analysis to guide project implementation |  |  |  | Ongoing | SNV |
|  |  | Awareness and sensitization of policies conducted with youth and local stakeholders |  |  |  | Ongoing | SNV |
|  |  | Community and household dialogues |  |  |  | Ongoing | SNV |
|  |  | Analysis of the implementation of key youth employment policies at local level done for identification of entry points. |  |  |  | Ongoing | SNV |
|  |  | Engagement with policymakers at all levels to influence change in policy implementation |  |  |  | Ongoing | SNV |
|  |  | Co-ordinated field monitoring visits by stakeholders |  |  |  | Ongoing | SNV |
| Ministry of Lands(MLAFWRD) | 1.Agriculture and food Security | Facilitate production and productivity of crops and small livestock in response to strategic food and nutrition priorities | Ward 1-29 30Tonnes of seed maize to 15000 farmers, 5 rain gauge to 5 institutions, Fingerling to 1 SBU and 2 farmers | Farmers, institutions and SBUs receive training and inputs distribution Farmer training, Presidential climate proofed input distribution. Small livestock training,Aquaculture training, (distribution of chicks, fingerlings and stock feed | Fuel, stationary | March 2025 | MLAFWRD |
|  |  | Conduct monitoring visits to Food Nutrition projects, Institutions, SBUs and Community Gardens | Ward 6, 10 and 25 | Number of sites-Joint monitoring at Provincial level | Fuel, lunch allowance, stationary | Monthly | MLAFWRD,DSD,MLGPW, HOCIC,ORAP,DCA,MoPSE,MOHCC |
|  |  | Participate in Food and Nutrition Security data collection, timely information dissemination, utilization and feedback | Ward 1-29 | Number of sectors participating in data collection, analysis, reporting and timely information dissemination, utilization and feedback | Fuel, lunch allowance, stationary | Ongoing | MLAFWRD,DSD |
|  |  | Farmer capacity building | Ward 1-29 | Number of farmers trained Number of technical demos Number of technical capacity building material developed, reviewed and disseminated | Fuel, stationary | Ongoing | MLAFWRD |
|  |  | Climate Smart Agricultural Practices | Ward 1-29 | Number of Pfumvudza/Intwasa plots and demo plots, Hydroponics in schools and institutions, Aquaculture in SBUs and peri-urban farmers | Fuel, stationary | Ongoing | MLAFWRD |
|  | Agriculture and food Security | Development of infrastructure (community gardens, hydroponics- youth hubs, greenhouses, fish ponds and small livestock) | Ward 1-29 | Number of community gardens established Number of hydroponics youth hubs developed Number of greenhouses(including institutions) Number of fish ponds Number of small livestock units established | Fuel, Stationary , lunch allowance | Ongoing | MLAFWRD |
|  | Agriculture and food Security | Cooking demonstrations | Ward 1-29 | Number cooking demos Number of recipe books developed and distributed | Fuel, Stationary, lunch allowance | Ongoing | MLAFWRD,MWACSMED |
|  |  | Promote and train on food processing &preservation of seasonal agriculture products. | Ward 1-29 | Number of farmers trained Number of farmers adopting technics | Fuel, Stationary | Ongoing | MLAFWRD (Mechanization Department) |
|  |  | Distribution of biofortified input packs | Ward 1-29 | Number of biofortified packs distributed | Fuel, Stationary | March | MLAFWRD |
|  |  | Training of farmers on farming as Business | Ward 1-29 | Number of farmers trained in farming as a Business Number of farmers adopting Farming as a Business | Fuel, Stationary | Ongoing | MLAFWRD (SPBD) ,MWACSMED |
|  |  | Nursery establishment in SBUs and Community gardens | Ward 8-22 | Number of vegetable nurseries established by system( conventional or float trays) | Fuel stationary | Ongoing | MLAFWR |